## Sheet1
Specific Action | Measurable | Achievable | Time | Responsibility | Status | Notes
The FCSA Climate Impact Society will create annual awareness campaigns that relate to sustainability and green initiatives. | We will measure this by tracking our annual campaigns, evaluate their success and how they correspond with susuatinability and green initiatives and student attitudes year on year. | On track to achieve with the current initiatives we have in place. | 2020-07-01 | FCSA Staff and FCSA Climate Impact society. |  | Tree planting 2020-2021 Second Saturday Squad 21-23 Grown your own Food and vape bins 23-24 Swap Shops 23-24, Swap Shops 24/25, Fabric and book Pumpkins, Braclet and Headband making, Sew a Scrunchie, Build a bike, Happy Habitats.
Every Campus will have an easily identifiable and regularly updated sustainability information point | The FCSA Digital Campus was established at the end of 2019 which allowed us to create a permanent digital space for Students interested in Climate Action as well as a noticeboard to all Students. Expanded our digital notices through partnership with internal comms, and digital services which allows us to add to the Student Portal and college TV screens. Created the FCSA Website in 2022 for updates and newsletters. Collaborated with the Sustainability team to acheive a permament space on Campus - The Climate Hub. | Achieved 2022 - Supported by the sustainability team. | 2022-09-01 | All Staff |  | Digital Campus, Internal TV Screens, Internal noticeboards, Digital student portal, FCSA Website - Awarness of students who know they exist through LS
The Green Club badges will be updated to match the new Climate Impact Society branding | Digital Badges for student volunteering - 3 levels | Due to be complete Summer 24 | 2024-08-01 | Craig Walker |  | Created October 24. Launched during SEM 1 24/45
All FCSA Branded Materials will be ethically sourced and made from recycled materials | Researching brands and organisations ethical and environmental commitments. Only purchasing items that are made from recycled materials or from ethical organisations | Transition over to sustainable clothing brand. Research affordable and sustainable items for FCSA Freebies. | 2020-07-01 | FCSA Manager and all staff who are approved to purchase. |  | FCSA clothing is sustainably sourced and made from recycled material. FCSA pens and other freshers freebies are all made from recycled materials and sent in recyclable packaging.
The FCSA Climate Impact Society will develop strong links with local and national organisations who have a focus on Sustainability | Groups are invited to attend FCSA Events such as Freshers and Re-Freshers. The FCSA CCO facilitates multiple Dr Bike Sessions with Greener Kirkcaldy througout the year. The FCSA CDC is developing community projects within nature spaces with Fife Council such at the unicorn trail and Riverside Park project. Sustainabilit Team and FCSA complete litter picks and apple picking with CLEAR Buckhaven as part of their community work. | Achieved with the Unicorn Trail, Bug hotels, Community Clean ups. Freshers and Re-freshers events have for the last two years providing interactive stalls and workships. Greener Kirkcaldy have done Student and Staff cooking workshops, free bike checks and free bike prpgrammes. | 2025-06-01 | FCSA Climate Impact Society and FCSA CDC |  | Climate Action Fife, Greener Kirkcaldy, CLEAR Buckhaven, EATS Rosyth, Fife Council Fife Coast and Countryside trust, Youth First,
FCSA Events a will be cost neutral | Untill 2020 the FCSA charged businesses to attend FCSA Events such as Freshers to keep our costs neutral, and maximise benefit to our students. However after the pandemic and the current Cost of Living Crisis, we have paused charging attendance at events to support local businesses and benefit our communities. | The FCSA had achieved this by 2020, however changed its policy to support the community. Currently we utilise External grants and funding to support our events and keep costs to a minimum. | 2025-06-01 | FCSA Team |  | Considering added a charge to corporate businesses and political parties to attend Freshers and Re-Freshers. Student Council input May 25
All students will have the opportunity to volunteer to benefit local communities across Fife | We will record the number of students who complete FCSA Internships, volunteer within the Second Saturday Squad, FCSA Societies, Liberation Groups and Events. | The FCSA host student internships every year, supporting students to achieve their community project assignments and work experience. The Second Saturday Squad is open to everyone to attend at scheduled events, or to create their own using our equipment. Students can volunteer to run societies, Liberation groups, and participate at external and internal events the FCSA and Fife College attend. | 2020-07-01 | FCSA Team
The FCSA will work alongside the Sustainability Team to deliver Climate Literacy Training for students | We will record the number of students who sign up and complete the training. | The course is currently being created, ready to launch AY 24/25 | 2024-09-01 | FCSA Team |  | Late to achieve, however training completed Sem 2 AY 24/25
The FCSA Climate impact Society will support the development of member led environmental and economic projects to benefit the local communities alongside sustainability partners | We will annually ask our students for suggestions and feedback on our community and environmental campaigns to ensure the needs of our students are being considered. We will engage in local community groups and sustainability organisations to gain their insight on current needs. | The Second Saturday Squad and Unicorn Trail were member led, environmentally concious and supported the local community. | 2023-07-01 | FCSA Team and FCSA Climate Impact Society. |  | Next big project will be Taylors Bus Campaign. Greener Kirkcaldy Build a Bike Sessions. FCSA CIS crop rotation and crafting.
The FCSA will achieve three external sustainability awards | We will record the number of submissions we enter, Shortlisted and Won. | On track to achieve with the current initiatives we have in place. | 2025-07-01 | FCSA Team |  | https://www.fc-sa.net/awards-we-ve-won Cycling Friendly Campus Award Most Enterprising Environmental individual. 2023, Green Gown Awards- Finalist 2024 GISU 'Excellent'
All FCSA staff will complete Climate Literacy Training | Each team member will enedevour to complete the training as it is rolled out across next 3 years | 3/6 staff completed or currently undertaking | 2025-07-01 | FCSA Team |  | Jade complete April 2024 Presidents Completing in June 2024. SEC on LTS. SACC and Manager Completed phase one 04/25
The FCSA will achieve a Green Impact Students Union Award | The FCSA for at least a 'Good/ Very Good' in their first submission with the goal of achieving 'Excellent' | On track to complete first submission | 2025-07-01 | Jade Burnett |  | Achieved Excellent in June 24
The FCSA will be Carbon Neutral and operating costs will be kept as low as possible | We will track vehicle milage from our use of the electric fleet and personal cars. We will used video calls as a first option. We will research our purchases and make ethical and cost effective purchases. | We operate using the College electric as a standard and only use our own cars as a last resort. We have not asked for a budget increase in the last three years, even with inflation we have utilised our resources and shared before buying new. We are paper free since 2016, in the event we do print it is on Recycled and Seeded paper. | 2025-07-01 | FCSA Staff and FCSA Manager
The FCSA will challenge local and national organisations to improve public transport for our Student, Staff and surrounding community | We will create a Campaign that captures the issues surrounding Public Transport for Fife, with a focus on Students accessibility. We will gather support from Students and Staff. We will present our findings to the Executive team, Board of Governors, Local Council and Government to gain support and long term change | FCSA President will lead on the campaign and put a motion to Student Council that the FCSA continues the work once their term is complete, if the project is not complete by the end of AY24/25. | 2025-07-01 | Taylor Edwards with the support of the FCSA Manager |  | President leading the campaign has left early, however the President of W&E has written a motion to present to Student Council in May to confirm they wish for the FCSA to continue this work.
The FCSA will continue to expand and improve its fleet ot E-bikes for students and staff hire | This will be measure by the number of bikes we purchase and improvments to our facilities within our campuses. Increased number of bike hires. | Apply for funding for the following; additional bikes and E-Bikes, Inclusive bikes | 2025-07-01 | CCO with support from the FCSA Manager |  | 40 E-Bikes plus 3 accessible bikes. Dunfermline Campus awarded cycling friendly campus award. Additional safe storage facilities at Glenrothes, Kirkcaldy and Dunfermline Campus. Improved changing and shower facilities at Dunfermline and Kirkcaldy. Additional lockers for cyclists in Dunfermline, Kirkcaldy and Glenrothes.